## Slide 1
James St. Subdivision Phase 2
Neighbourhood Construction
July 2023

## Slide 2: Welcome & Introductions
Presenters today are:
Karla Bailey, Vice President, System Planning Asset Management & Engineering
Mitch Dziurda, Design Engineer
Notes: Christina

## Slide 3: James St. Subdivision Project Extents
Simon Fraser Dr.
Champlain Pl.
Churchill Dr.
Redwood Ave.
Notes: Colored lines indicate where new poles and wires will be, a full pdf map will be posted on the website for download and viewing afterwards.
Notice that Synergy North poles and wires are located in backyard easements throughout the area

## Slide 4
Synergy North Owned Assets
Transformer
Wires
Pole
Meter Base
Transformer
Anchor
Notes: What we own – meters, transformers wires, poles
What we do not own – telecom boxes and wires on the bottom

## Slide 5
What to expect when we’re in your neighbourhood
Padmount Transformer Replacement
  Excavation
  Settling and backfill material
  Access and Cranes
  Outages
  Occur during service changes
  Traffic disruptions
  Follow traffic rules, no closing of roads
  Noise
  OHSA guidelines
Notes: Padmount - excavation can be several meters around the existing transformer location
-Backfill material mounded to accommodate for settling
- Designated utility easement, SNC will be using cranes
Outages - Receive notice with point of contact if questions
Traffic - Several Vehicles, some will be subcontractors
- In construction zones – please slow down
Noise - Crews operate during 8-4 and follow the occupational health and safety act
Access -through driveways and yards

## Slide 6
Forestry
  Notices
  Will be sent to all customers prior to trimming
  Encouraged to contact SNC to provide comments and discuss options for trees
  Trimming
  Site visits for vegetation that requires trimming
  Trees could be cleared up to 3m to provide access to padmounted equipment
  All clippings will be cleaned and cleared
Notes: 1) Mail out notices to customers in project
2) Upon completion of a site visit Synergy North will determine the scope of work for each property
3) Customers will be contacted via mail and telephone to consult on the scope of work

## Slide 7
Forestry
  “Plant the right tree in the right place”
  Appropriate types, sizes, locations
Notes: When looking at landscaping options, remember to consider height and location
Look at the mature height when planting near power lines and plant taller trees away from lines and only low compact species new power lines.
Coordinate with City of Thunder Bay on planting in boulevards

## Slide 8: James St. Subdivision
Statistics
  Residential, 114 customers
  13 new padmount transformers
  ~2,207m of refurbished cable
  Total project cost : $700,000
Notes: Cost includes equipment, labour, trucking

## Slide 9
Typical Design Practices
Typical underground projects are designed in a “like-for-like” manner
  New equipment locations remain as close as practical to existing locations
  Obstructions
Notes: “like-for-like” means that we replace it in the location where it existed, but for current standards and loads

## Slide 10: James St. Subdivision Project Extents
Simon Fraser Dr.
Champlain Pl.
Churchill Dr.
Redwood Ave.
Notes: Colored lines indicate where new poles and wires will be, a full pdf map will be posted on the website for download and viewing afterwards.
Notice that Synergy North transformers are located in backyard easements throughout the area

## Slide 11
System Changes highlighted
Orange
  New pole, anchor or wire in a location where it did not exist prior
Blue
  Moving overhead wires underground or underground replacement
Green
  Change to the existing plant, extra wire or pole shift less than 5m
Notes: Show a series of maps indicating where our replacement is not a “like-for-like” replacement

## Slide 12: Blue Changes (transformer replacement)

## Slide 13: Blue Changes (transformer replacement)

## Slide 14: Blue Changes (transformer replacement)

## Slide 15
Schedule
  2023
  Forestry (As Needed)
  Surveying (Completed)
  Site visits (Early August)
  Transformer Replacement (September/October)
Notes: Certain types of work are seasonal – ie. with reference to leaves on trees and when the ground is thawed and dry
Explain Surveying
Our timing can change based on snow thaw and freeze

## Slide 16
When You Can Expect To Hear From Us
Neighbourhood Meeting
Optional Forestry Notice (phone call or email)
Obstruction Notice – (phone call or letter mail)
Notice of Project (letter mail – 3 weeks prior to construction )
Outage Notice (letter mail or automated call)
Notes: When you can expect to hear from Synergy North
Neighbourhood meeting before any work to begin
Forestry notice if trees being cut 2-3 weeks before cut
Notice of Project is usually 3 weeks before construction – next year
Obstructions notice - which doesn’t allow us to access existing pole location or new pole location
Outage notice is one week letter mail and automated call